## Functional
Areas | Requirements | JIRA Issue type | JIRA Id | Lead | Owner | Sqaud | Dev Status | Dev Estimation | Dev Start Date | Dev End Date | Test Status | Test Estimation | Test Start Date | Test End Date
IB Fixes | SMTP | Improvement |  | Anant M | Amir | DoseWatch | In Progress
| FFPR delay | Improvement |  | Krishna | Krishna | Datalink | Dev Done | 0
| FPPR HTTPS | Improvement |  | Krishna | Vikas | Datalink | Blocked | 15 | 2026-08-17 | 2026-08-28
| DRL Belgium | Improvement |  | Saurabh | Anant Singh | DoseWatch | Dev Done | 0
| DRL UK | Improvement |  | Saurabh | Praveen | DoseWatch | Blocked | 2 | 2026-08-10 | 2026-08-12
| DRL Denmark | Improvement |  | Saurabh | Praveen | DoseWatch | In Progress | 3 | 2026-08-13 | 2026-08-18
| DRL Romania | Improvement |  | Saurabh | Praveen | DoseWatch | Blocked | 5 | 2026-08-19 | 2026-08-27
| DRL Poland | Improvement |  | Saurabh | Praveen | DoseWatch | In Progress | 2 | 2026-08-28 | 2026-09-01
| DRL Germany | Improvement |  | Saurabh | Anant Singh | DoseWatch | Not Started | 2 | 2026-08-10 | 2026-08-12
| CT Dose Performance | Bug |  | Saurabh | Saleem | DoseWatch | In Progress | 3 | 2026-08-10 | 2026-08-13
MMSR/Pen quiz fixes | FIS Algorithm - MSSR 4499 &MMSR -9 | Improvement |  | Krishna | Calvin | Datalink | Dev Done | 0
| Hardcoded Encryption key - MMSR 6699 & MMSR -3 | Improvement |  | Krishna | Calvin | Datalink | Dev Done | 0
| Unchanged default password MMSR -6703 & MSSR | Improvement |  | Krishna | Krishna | Datalink | Dev Done | 0
| MMSR - 4494 Unencrypted defautl database password | Improvement |  | Krishna | Krishna | Datalink | Dev Done | 0
| MMSR 21 - Product Security Life Cycle Compliance [ RSVP] | Improvement |  | Krishna | Sushma | Datalink | Blocked | 2
| MMSR 4 - All passwords can be changed | Improvement |  | Krishna | Krishna | Datalink | Dev Done | 0
DAST/SAST fixes | SAST - Raboit- MQ/Erlang | Improvement |  | Saurabh | Praveen | DoseWatch | Dev Done | 0
| SAST - Python upgrade for GEMedia service | Improvement |  | Saurabh | Anant Singh | DoseWatch | Dev Done | 0
| SAST - Artemis upgrade | Improvement |  | Krishna | Calvin | DoseWatch
| DAST - SQL injection | Improvement |  | Krishna | Sushma | Datalink | No Fix | 0
| DAST - LDAP injection | Improvement |  | Krishna | Vikas | Datalink | No Fix | 0
| DAST - Medium password in response | Improvement |  | Krishna | Vikas | Datalink | Dev Done | 0
DC fixes | Quartz Scheduler | Improvement |  | Saurabh | Saleem | DoseWatch | Not Started | 5 | 2026-08-14 | 2026-08-24
| Netty (transport, codec-http2, codec-dns, resolver-dns, transport-native-unix-common) | Improvement |  | Krishna | Calvin | DoseWatch | In Progress
| Axios | Improvement |  | Krishna | Vikas | DoseWatch | In Progress
| Apache Tomcat (embedded core) | Improvement |  | Saurabh | Anant Singh | DoseWatch | Not Started | 2 | 2026-08-13 | 2026-08-17
| Apache CXF (core, databinding-aegis, features-clustering, ws-security, services-sts-core, tools-validator, tools-wsdlto-core) | Improvement |  | Saurabh | Anant Singh | DoseWatch | Not Started | 5 | 2026-08-18 | 2026-08-26
| Lodash / lodash-es | Improvement |  | Saurabh | Anant Singh | DoseWatch | Not Started | 2 | 2026-08-27 | 2026-08-31
| Handlebars | Improvement |  | Saurabh | Anant Singh | DoseWatch | Not Started | 2 | 2026-09-01 | 2026-09-03
| openbao-client-model (internal) | Improvement |  | Saurabh | Anant Singh | DoseWatch | Not Started | 2 | 2026-09-04 | 2026-09-08
| DOMPurify (via swagger-ui) | Improvement |  | Saurabh | Anant Singh | DoseWatch | Not Started | 2 | 2026-09-09 | 2026-09-11
| Spring Framework (spring-core) | Improvement |  | Saurabh | Saleem | DoseWatch | Not Started | 3 | 2026-08-25 | 2026-08-28
| Thymeleaf | Improvement |  | Saurabh | Saleem | DoseWatch | Not Started | 2 | 2026-08-31 | 2026-09-02
| mchange-commons-java | Improvement |  | Saurabh | Praveen | DoseWatch | Not Started | 5 | 2026-09-02 | 2026-09-10
| GlassFish JAXB core | Improvement |  | Saurabh | Praveen | DoseWatch | Not Started | 2 | 2026-09-11 | 2026-09-15
| ActiveMQ Artemis (8 modules) | Improvement |  | Saurabh | Praveen | DoseWatch | Not Started | 2 | 2026-09-16 | 2026-09-18
| Undertow (core, servlet, websockets-jsr) | Improvement |  | Saurabh | Praveen | DoseWatch | Not Started | 2 | 2026-09-21 | 2026-09-23
| flatted / flat (npm) | Improvement |  | Saurabh | Praveen | DoseWatch | Not Started | 2 | 2026-09-24 | 2026-09-28
| i18next-http-backend | Improvement |  | Saurabh | Praveen | DoseWatch | Not Started | 2 | 2026-09-29 | 2026-10-01
| assertj-core | Improvement |  | Saurabh | Amir | DoseWatch | Not Started | 5 | 2026-08-10 | 2026-08-18
| opener (npm) | Improvement |  | Saurabh | Amir | DoseWatch | Not Started | 2 | 2026-08-19 | 2026-08-21
| @angular/core | Improvement |  | Saurabh | Amir | DoseWatch | Not Started | 2 | 2026-08-24 | 2026-08-26
| getobject (npm) | Improvement |  | Saurabh | Amir | DoseWatch | Not Started | 2 | 2026-08-27 | 2026-08-31
| minimist (npm) | Improvement |  | Saurabh | Amir | DoseWatch | Not Started | 2 | 2026-09-01 | 2026-09-03
| grpc-api | Improvement |  | Saurabh | Amir | DoseWatch | Not Started | 2 | 2026-09-04 | 2026-09-08
| jgroups-aws | Improvement |  | Saurabh | Amir | DoseWatch | Not Started | 2 | 2026-09-09 | 2026-09-11
PET/CT changes | SD-18624: PET/CT : Device Classification | Improvement |  | Saurabh | Saurabh | DoseWatch | Dev Done | 0
| SD-18610: PET/CT Series Duration Calculation at DoseWatch | Improvement |  | Saurabh | Saurabh | DoseWatch | In Progress | 5 | 2026-08-10 | 2026-08-26
| PET/CT Filter out of reconstructed series | Improvement |  | Saurabh | Saleem | DoseWatch | Dev Done | 0
| PET/CT Populate unified device names for the 2 different AET’s | Improvement |  | Saurabh | Saurabh | DoseWatch | Dev Done | 0
Iguana replacement | Migration of IGUANA ATD script to Mirth ATD Scripts | Improvement |  | Krishna | Calvin | Datalink | Not Started | 3 | 2026-08-10 | 2026-08-12
| Migration of IGUANA SCH script to Mirth SCH Scripts | Improvement |  | Krishna | Calvin | Datalink | Not Started | 3 | 2026-08-13 | 2026-08-17
| Migration of IGUANA ORM script to Mirth ORM Scripts | Improvement |  | Krishna | Calvin | Datalink | Not Started | 3 | 2026-08-18 | 2026-08-20
| Migration of IGUANA ORU script to Mirth ORU Scripts | Improvement |  | Krishna | Vikas | Datalink | Not Started | 2 | 2026-08-21 | 2026-08-25
| Migration of IGUANA FHIR script to Mirth FHIR Scripts | Improvement |  | Krishna | Vikas | Datalink | Not Started | 3 | 2026-08-26 | 2026-08-29
| Migration of IGUANA PIX script to Mirth PIX Scripts | Improvement |  | Krishna | Vikas | Datalink | Not Started | 3 | 2026-08-31 | 2026-09-02
| Migration of IGUANA PDQ script to Mirth PDQ Scripts | Improvement |  | Krishna | Krishna | Datalink | Not Started | 3 | 2026-09-03 | 2026-09-07
| Migration of IGUANA PDX script to Mirth PDX Scripts | Improvement |  | Krishna | Krishna | Datalink | Not Started | 3 | 2026-09-08 | 2026-09-10
Installer | Update installer to bundle Mirth scripts | Improvement |  | Krishna | Calvin | Datalink | Not Started | 4 | 2026-09-11 | 2026-09-16
| Update installer for in bound and out bound channel creation | Improvement |  | Krishna | Calvin | Datalink | Not Started | 4 | 2026-09-17 | 2026-09-22
| Data dictionaries installer for DRL | Improvement |  | Saurabh | Anant Singh | DoseWatch | In Progress | 3 | 2026-09-14 | 2026-09-17
| Data dictionaries installer for PET-CT | Improvement |  | Saurabh | Saurabh | DoseWatch | Dev Done | 2
| Update migration script for DB changes | Improvement |  | Krishna | Krishna | Datalink | Dev Done | 0
| Update installer for OpenBoa changes | Improvement |  | Krishna | Krishna | Datalink | Dev Done | 0
| Update installer for Artimus changes | Improvement |  | Krishna | Calvin | Datalink | Dev Done | 0
Release readiness | Candidate build creation | Improvement |  | Saurabh | Saleem/Vikas | DoseWatch/DataLink |  | 5 | 2026-10-22 | 2026-10-30
V&V Bugs | All Bug fix timing | Bug |  | Saurabhj/Krishna/Anant M |  | DoseWatch/DataLink | Not Started

## Documentation
Document | Owner | Contributors | Reviewer | Approver
SOUP
TDR- security changes, SMPT, IGUANA replacement
DFMEA
IGUANA interface manual
SRS

## DWIB
Work Areas | Work Items | Owner | Estimations | Required for DW 3.4.2.1
Monitoring Agent Impact due to OpenBao | Hard coded credentials (MMSR) | Anant Mishra
| Hard coded encrption keys(MMSR) | Anant Mishra
| Veracode reported issue fixes | Anant Mishra
DWIB Debug setup | Setting up the DWIB dev debug setup with DoseWatch integration | Anant Mishra
DWIB Jenkins build/Pipelines setup and testing | Generating prod ready DWIB build and CI testing | Anant Mishra

## Jira Stories
Area | Requirement | Owner | Story Title | Description | Acceptance Criteria (Given/When/Then) | Dependencies | Out of Scope | Story Points | Target Start Date | Target End Date
IB Fixes | DRL Germany | Anant Singh | Add DRL data dictionary for Germany | DoseWatch needs country-specific Dose Reference Level (DRL) data to benchmark radiation dose against national reference values. This story adds the Germany DRL data dictionary, following the pattern used for Belgium, UK, Denmark, Romania and Poland. | 1. Given the Germany DRL reference dataset, When it is loaded into DoseWatch, Then Germany appears as a selectable country with correct DRL values per exam/protocol. 2. Given a study performed at a facility configured for Germany, When dose data is evaluated, Then it is compared against the correct Germany DRL thresholds. 3. Given the configuration is validated, When compared to the official German DRL reference table, Then no discrepancies are found. | Official Germany DRL reference dataset/values | DRL configuration for countries other than Germany | 2 | 2026-08-10 | 2026-08-12
DC fixes | Quartz Scheduler | Saleem | Upgrade Quartz Scheduler library version | The Quartz Scheduler dependency used for job scheduling in DoseWatch is flagged in security scans for known vulnerabilities. This story upgrades it to a patched version to remediate the findings. | 1. Given the current Quartz Scheduler version, When it is upgraded to the patched release, Then the application builds and all scheduled jobs continue to run without failure. 2. Given the upgrade is complete, When the security scan is re-run, Then no Quartz Scheduler related vulnerabilities are reported. 3. Given existing scheduled jobs, When regression tested, Then job triggers, execution order and timing behave exactly as before. | None | Redesigning job scheduling logic | 5 | 2026-08-14 | 2026-08-24
DC fixes | Apache Tomcat (embedded core) | Anant Singh | Upgrade embedded Apache Tomcat core | The embedded Apache Tomcat server used by DoseWatch has known vulnerabilities flagged in security scanning. This story upgrades Tomcat core to a secure version. | 1. Given the current Tomcat version, When upgraded, Then the application starts and serves requests without errors. 2. Given the upgrade, When the security scan is re-run, Then no Tomcat-related CVEs remain open. 3. Given core application flows, When regression tested, Then no functional or performance regression is observed. | None | Application server architecture changes | 2 | 2026-08-13 | 2026-08-17
DC fixes | Apache CXF (core, databinding-aegis, features-clustering, ws-security, services-sts-core, tools-validator, tools-wsdlto-core) | Anant Singh | Upgrade Apache CXF web service modules | Seven Apache CXF modules used for web services are flagged with known vulnerabilities. This story upgrades all affected CXF modules together to secure versions. | 1. Given the current CXF module versions, When all listed modules are upgraded, Then all SOAP/web service endpoints build and start successfully. 2. Given the upgraded modules, When security scans are re-run, Then no CXF-related vulnerabilities remain. 3. Given existing web service consumers, When regression tested, Then requests/responses and WS-Security behavior are unchanged. | Compatibility verification across the 7 CXF modules | Migration to a different web services framework | 5 | 2026-08-18 | 2026-08-26
DC fixes | Lodash / lodash-es | Anant Singh | Upgrade Lodash / lodash-es library | The Lodash and lodash-es utility libraries used in the DoseWatch UI are flagged for known vulnerabilities. This story upgrades both to secure versions. | 1. Given the current versions, When upgraded, Then the UI builds without errors. 2. Given the upgrade, When security scans re-run, Then no Lodash-related vulnerabilities remain. 3. Given UI functions using Lodash utilities, When regression tested, Then behavior is unchanged. | None | Refactoring code away from Lodash usage | 2 | 2026-08-27 | 2026-08-31
DC fixes | Handlebars | Anant Singh | Upgrade Handlebars templating library | The Handlebars library used for template rendering is flagged with known vulnerabilities. This story upgrades Handlebars to a secure version. | 1. Given the current version, When upgraded, Then all templates render correctly. 2. Given the upgrade, When security scans re-run, Then no Handlebars vulnerabilities remain. 3. Given existing templated pages, When regression tested, Then rendered output is unchanged. | None | Template engine replacement | 2 | 2026-09-01 | 2026-09-03
DC fixes | openbao-client-model (internal) | Anant Singh | Upgrade openbao-client-model internal library | The internal openbao-client-model dependency, used for secrets/vault client integration, is flagged for known vulnerabilities. This story upgrades it to a secure version. | 1. Given the current version, When upgraded, Then the application successfully authenticates and retrieves secrets from OpenBao. 2. Given the upgrade, When security scans re-run, Then no related vulnerabilities remain. 3. Given secret retrieval flows, When regression tested, Then no functional regression is observed. | Availability of a compatible OpenBao server-side version | Migration to a different secrets management solution | 2 | 2026-09-04 | 2026-09-08
DC fixes | DOMPurify (via swagger-ui) | Anant Singh | Upgrade DOMPurify used by Swagger UI | The DOMPurify library bundled with Swagger UI is flagged with known vulnerabilities. This story upgrades DOMPurify (directly or via a Swagger UI update) to a secure version. | 1. Given the current version, When upgraded, Then the Swagger UI/API docs page loads and sanitizes content correctly. 2. Given the upgrade, When security scans re-run, Then no DOMPurify vulnerabilities remain. 3. Given API documentation pages, When regression tested, Then rendering and functionality are unchanged. | Swagger UI version compatibility | Replacing Swagger UI with another API doc tool | 2 | 2026-09-09 | 2026-09-11
DC fixes | Spring Framework (spring-core) | Saleem | Upgrade Spring Framework spring-core module | The spring-core module is flagged with known vulnerabilities in security scans. This story upgrades spring-core to a patched version. | 1. Given the current version, When upgraded, Then the application context loads and all Spring-managed beans initialize successfully. 2. Given the upgrade, When security scans re-run, Then no spring-core vulnerabilities remain. 3. Given core application services, When regression tested, Then no functional regression is observed. | Compatibility with other Spring modules in use | Migration to a different application framework | 3 | 2026-08-25 | 2026-08-28
DC fixes | Thymeleaf | Saleem | Upgrade Thymeleaf templating engine | The Thymeleaf library used for server-side page rendering is flagged with known vulnerabilities. This story upgrades Thymeleaf to a secure version. | 1. Given the current version, When upgraded, Then all Thymeleaf-rendered pages load correctly. 2. Given the upgrade, When security scans re-run, Then no Thymeleaf vulnerabilities remain. 3. Given existing rendered pages, When regression tested, Then output markup and behavior are unchanged. | Compatibility with Spring Framework version in use | Migration to a different templating engine | 2 | 2026-08-31 | 2026-09-02
DC fixes | mchange-commons-java | Praveen | Upgrade mchange-commons-java library | The mchange-commons-java library, used by the connection pooling layer, is flagged with known vulnerabilities. This story upgrades it to a secure version. | 1. Given the current version, When upgraded, Then database connection pooling initializes and functions correctly. 2. Given the upgrade, When security scans re-run, Then no mchange-commons-java vulnerabilities remain. 3. Given existing database operations, When regression tested, Then no connectivity or performance regression is observed. | Compatibility with the connection pool provider (e.g., c3p0) in use | Replacing the connection pooling library | 5 | 2026-09-02 | 2026-09-10
DC fixes | GlassFish JAXB core | Praveen | Upgrade GlassFish JAXB core library | The GlassFish JAXB core library, used for XML binding, is flagged with known vulnerabilities. This story upgrades it to a secure version. | 1. Given the current version, When upgraded, Then XML marshalling/unmarshalling operations complete successfully. 2. Given the upgrade, When security scans re-run, Then no JAXB-related vulnerabilities remain. 3. Given existing XML-dependent integrations, When regression tested, Then output is unchanged. | None | Migration to a different XML binding library | 2 | 2026-09-11 | 2026-09-15
DC fixes | ActiveMQ Artemis (8 modules) | Praveen | Upgrade ActiveMQ Artemis messaging modules | Eight ActiveMQ Artemis modules used for messaging are flagged with known vulnerabilities. This story upgrades all affected modules together to secure versions. | 1. Given the current module versions, When all 8 modules are upgraded, Then the message broker starts and processes messages successfully. 2. Given the upgrade, When security scans re-run, Then no Artemis-related vulnerabilities remain. 3. Given existing producers/consumers, When regression tested, Then message delivery and ordering are unaffected. | Compatibility across all 8 Artemis modules | Migration to a different messaging broker | 2 | 2026-09-16 | 2026-09-18
DC fixes | Undertow (core, servlet, websockets-jsr) | Praveen | Upgrade Undertow web server modules | The Undertow core, servlet, and websockets-jsr modules are flagged with known vulnerabilities. This story upgrades all three modules to secure versions. | 1. Given the current versions, When all modules are upgraded, Then the application server starts and serves HTTP/WebSocket requests correctly. 2. Given the upgrade, When security scans re-run, Then no Undertow-related vulnerabilities remain. 3. Given existing WebSocket and HTTP flows, When regression tested, Then behavior is unchanged. | None | Replacing Undertow with a different embedded server | 2 | 2026-09-21 | 2026-09-23
DC fixes | flatted / flat (npm) | Praveen | Upgrade flatted / flat npm packages | The flatted and flat npm packages used for object serialization are flagged with known vulnerabilities. This story upgrades both to secure versions. | 1. Given the current versions, When upgraded, Then the UI build completes without errors. 2. Given the upgrade, When security scans re-run, Then no flatted/flat vulnerabilities remain. 3. Given features relying on these packages, When regression tested, Then serialization/deserialization behavior is unchanged. | None | Removing dependency usage from codebase | 2 | 2026-09-24 | 2026-09-28
DC fixes | i18next-http-backend | Praveen | Upgrade i18next-http-backend package | The i18next-http-backend npm package used for loading translation files is flagged with known vulnerabilities. This story upgrades it to a secure version. | 1. Given the current version, When upgraded, Then translation files load correctly for all supported locales. 2. Given the upgrade, When security scans re-run, Then no i18next-http-backend vulnerabilities remain. 3. Given existing localized UI screens, When regression tested, Then translations display correctly. | None | Adding new language/locale support | 2 | 2026-09-29 | 2026-10-01
DC fixes | assertj-core | Amir | Upgrade AssertJ core test library | The assertj-core library used in automated test assertions is flagged with known vulnerabilities. This story upgrades it to a secure version. | 1. Given the current version, When upgraded, Then the full automated test suite compiles and executes successfully. 2. Given the upgrade, When security scans re-run, Then no assertj-core vulnerabilities remain. 3. Given existing test cases, When executed, Then all assertions pass with the same results as before the upgrade. | None | Rewriting existing test assertions | 5 | 2026-08-10 | 2026-08-18
DC fixes | opener (npm) | Amir | Upgrade opener npm package | The opener npm package, used for opening URLs/files from Node tooling, is flagged with known vulnerabilities. This story upgrades it to a secure version. | 1. Given the current version, When upgraded, Then build/dev tooling that relies on opener continues to function. 2. Given the upgrade, When security scans re-run, Then no opener-related vulnerabilities remain. 3. Given the build pipeline, When executed, Then no new errors are introduced. | None | Changes to build tooling architecture | 2 | 2026-08-19 | 2026-08-21
DC fixes | @angular/core | Amir | Upgrade @angular/core framework version | The @angular/core package is flagged with known vulnerabilities in security scans. This story upgrades Angular core (and required peer dependencies) to a secure version. | 1. Given the current version, When upgraded, Then the DoseWatch UI application builds and starts without errors. 2. Given the upgrade, When security scans re-run, Then no @angular/core vulnerabilities remain. 3. Given key UI workflows, When regression tested, Then no functional or visual regression is observed. | Compatibility of other Angular ecosystem packages with the new core version | Migration to a different frontend framework | 2 | 2026-08-22 | 2026-08-26
DC fixes | getobject (npm) | Amir | Upgrade getobject npm package | The getobject npm package is flagged with known vulnerabilities. This story upgrades it to a secure version. | 1. Given the current version, When upgraded, Then the build completes without errors. 2. Given the upgrade, When security scans re-run, Then no getobject-related vulnerabilities remain. 3. Given features using getobject, When regression tested, Then behavior is unchanged. | None | Removing dependency usage from codebase | 2 | 2026-08-27 | 2026-08-29
DC fixes | minimist (npm) | Amir | Upgrade minimist npm package | The minimist npm package used for CLI argument parsing is flagged with known vulnerabilities. This story upgrades it to a secure version. | 1. Given the current version, When upgraded, Then build and CLI tooling that depend on minimist continue to work. 2. Given the upgrade, When security scans re-run, Then no minimist-related vulnerabilities remain. 3. Given the build pipeline, When executed, Then no new errors are introduced. | None | Replacing the CLI parsing library | 2 | 2026-08-31 | 2026-09-02
DC fixes | grpc-api | Amir | Upgrade grpc-api library | The grpc-api dependency used for gRPC service communication is flagged with known vulnerabilities. This story upgrades it to a secure version. | 1. Given the current version, When upgraded, Then gRPC services build and start successfully. 2. Given the upgrade, When security scans re-run, Then no grpc-api vulnerabilities remain. 3. Given existing gRPC calls, When regression tested, Then request/response behavior is unchanged. | Compatibility with other gRPC ecosystem libraries in use | Migration to a different RPC framework | 2 | 2026-09-03 | 2026-09-05
DC fixes | jgroups-aws | Amir | Upgrade jgroups-aws clustering library | The jgroups-aws library, used for cluster discovery on AWS, is flagged with known vulnerabilities. This story upgrades it to a secure version. | 1. Given the current version, When upgraded, Then cluster nodes discover and join each other correctly on AWS. 2. Given the upgrade, When security scans re-run, Then no jgroups-aws vulnerabilities remain. 3. Given a multi-node deployment, When regression tested, Then clustering and failover behavior are unchanged. | AWS environment/IAM permissions unchanged | Migration to a different clustering mechanism | 2 | 2026-09-08 | 2026-09-10